## Basic Gantt Chart
SMART BALLOT BOX GANTT CHART
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | JAN | FEB | MAR | APR | MAY | JUN
Project Planning
| Meet With Sponsor (Weekly/BI-Weekly Meetings) | 2020-01-05 | 2020-01-10 | 0 | 6 | Ali, Nick, Jonathan, Jiaqi
| Meet With Advisor (Weekly Friday Meetings) | 2020-01-07 | 2020-01-10 | 2 | 4 | Ali, Nick, Jonathan, Jiaqi
| Meet With Team (Weekly Team Meetings) | 2020-01-07 | 2020-01-10 | 2 | 4 | Ali, Nick, Jonathan, Jiaqi
| Set Up Team Collaboration Site (Github/Google Drive, KeyBase) | 2020-01-07 | 2020-01-10 | 2 | 4 | Ali, Nick, Jonathan, Jiaqi
| Research Previous Work Completed (Ex. Original Functionality of SBB2019, Github, Documentation, Schematics, etc...) | 2020-01-10 | 2020-01-14 | 5 | 5 | Ali, Nick, Jonathan, Jiaqi
| Research How We Will Add to Project (How to make it more cost-effective) | 2020-01-14 | 2020-01-20 | 9 | 7 | Ali, Nick, Jonathan, Jiaqi
| Decide What Items are Wants vs Needs (Ex. Requirements/Specifications, Should/Must/May) | 2020-01-20 | 2020-01-24 | 15 | 5 | Jonathan
| Research Which Processor To Use (We chose the Arduino UNO) | 2020-01-20 | 2020-01-24 | 15 | 5 | Ali, Nick, Jonathan, Jiaqi
| Update Collaboration Site (Weekly) | 2020-01-24 | 2020-01-31 | 19 | 8 | Ali, Nick, Jonathan, Jiaqi
| First Draft Of Proposal | 2020-01-24 | 2020-01-31 | 19 | 8 | Ali
| First Draft Of Project Schedule And Tasks | 2020-01-24 | 2020-01-31 | 19 | 8 | Nick
| Decide How To Recreate The SBB With COTS Parts | 2020-02-01 | 2020-02-07 | 27 | 7 | Ali, Nick, Jonathan, Jiaqi
| Second Draft of Proposal | 2020-01-31 | 2020-02-07 | 26 | 8 | Ali
| Finalize Proposal | 2020-02-08 | 2020-02-21 | 34 | 14 | Ali, Nick, Jonathan, Jiaqi
| Finalize Project Schedule | 2020-02-14 | 2020-02-21 | 40 | 8 | Ali, Nick, Jonathan, Jiaqi
| Order Parts | 2020-02-21 | 2020-02-28 | 47 | 8 | Ali
System Architecture
| Review Existing Code Base (Software) | 2020-02-21 | 2020-03-01 | 47 | 10 | Ali, Nick
| Figure Out The Connections Of The CASCADIO Board (Hardware) | 2020-02-28 | 2020-03-15 | 54 | 17 | Jonathan, Jiaqi
| Figuring Out What Code Needs to Change (Software) | 2020-02-21 | 2020-03-08 | 47 | 17 | Ali, Nick
| Upload Documentation For Code and CASCADIO Board Connections | 2020-03-15 | 2020-03-21 | 70 | 7 | Ali, Nick, Jonathan, Jiaqi
| Figure out I/O For Arduino to Interact with CASCADIO Board (Hardware) | 2020-03-01 | 2020-03-13 | 56 | 13 | Ali, Nick, Jonathan, Jiaqi
| Figure Out How CASCADIO Board Works (Hardware) | 2020-03-21 | 2020-04-05 | 76 | 16 | Jonathan, Jiaqi
| Upload Documentation for Code and Hardware | 2020-03-21 | 2020-03-23 | 76 | 3 | Ali, Nick, Jonathan, Jiaqi
| Figure Out How To Create Barcode For Ballot (Hardware/Software) | 2020-03-21 | 2020-03-27 | 76 | 7 | Ali, Nick, Jonathan, Jiaqi, Joe
| Redesign FreeRTOS Code To Fit Our Processor (Software) | 2020-03-08 | 2020-04-12 | 63 | 36 | Ali, Nick
| Re-Finalize Project Proposal/Schedule | 2020-04-03 | 2020-04-05 | 89 | 3 | Ali, Nick, Jonathan, Jiaqi
| Peer Code Review | 2020-04-12 | 2020-04-14 | 98 | 3 | Ali, Nick, Jonathan, Jiaqi, Tom,(Maybe Joe)
| Upload Documentation For Code and Hardware | 2020-04-12 | 2020-04-15 | 98 | 4 | Ali, Nick, Jonathan, Jiaqi
| Redesign Firmware Code To Fit Our Processor (Software) | 2020-04-15 | 2020-05-02 | 101 | 18 | Ali, Nick
| Peer Code Review | 2020-05-02 | 2020-05-03 | 118 | 2 | Ali, Nick, Jonathan, Jiaqi, Tom,(Maybe Joe)
| Redesign SSB Software to Fit Our Processor (Software) | 2020-05-03 | 2020-05-23 | 119 | 21 | Ali, Nick
| Peer Code Review | 2020-05-23 | 2020-05-24 | 139 | 2 | Ali, Nick, Jonathan, Jiaqi, Tom,(Maybe Joe)
| Upload Documentation For Code and Hardware | 2020-05-24 | 2020-05-29 | 140 | 6 | Ali, Nick, Jonathan, Jiaqi
System Design and Validation
| Test the Functionallity of the Software (Test As We Go!) | 2020-03-10 | 2020-05-24 | 65 | 76 | Ali, Nick
| Make Sure Each I/O Is Connected To The Proper Port | 2020-03-10 | 2020-03-21 | 65 | 12 | Ali, Nick
| Correct FreeRTOS Working Properly on UNO | 2020-03-22 | 2020-04-15 | 77 | 25 | Ali, Nick
| SBB Software Working Properly on UNO | 2020-04-15 | 2020-05-02 | 101 | 18 | Ali, Nick
| UNO Has The Correct Firmware | 2020-05-02 | 2020-05-24 | 118 | 23 | Ali, Nick
| Test the Functionality of the Hardware (Test As We Go!) | 2020-03-01 | 2020-05-24 | 56 | 85 | Jonathan, Jiaqi
| LCD Screen Performance Testing | 2020-04-06 | 2020-04-10 | 92 | 5 | Jonathan, Jiaqi
| Power Supply Performance Testing | 2020-04-10 | 2020-04-15 | 96 | 6 | Jonathan, Jiaqi
| Real Time Clock Performance Testing | 2020-04-15 | 2020-04-22 | 101 | 8 | Jonathan, Jiaqi
| MicroSD Card Performance Testing | 2020-04-23 | 2020-04-25 | 109 | 3 | Jonathan, Jiaqi
| Test interactions between each unit | 2020-04-25 | 2020-04-27 | 111 | 3 | Jonathan, Jiaqi
| Barcode Scanner Testing | 2020-04-27 | 2020-04-29 | 113 | 3 | Jonathan, Jiaqi
| Cast or Spoil Performance Testing | 2020-04-29 | 2020-05-01 | 115 | 3 | Jonathan, Jiaqi
| Create Ballots with Barcodes | 2020-05-01 | 2020-05-06 | 117 | 6 | Jonathan, Jiaqi
MVP Implementation
| Finish Up Documentation | 2020-05-06 | 2020-05-29 | 122 | 24 | Ali, Nick, Jonathan, Jiaqi
| Make Sure Collaboration Site Is Up To Date | 2020-05-06 | 2020-05-29 | 122 | 24 | Jonathan, Jiaqi
| Make Sure All Code Is Commented and Formatted Properly | 2020-05-07 | 2020-05-29 | 123 | 23 | Ali, Nick
| Finish Up Report | 2020-05-11 | 2020-05-29 | 127 | 19 | Ali, Nick, Jonathan, Jiaqi
| Finalize Working Prototype | 2020-05-05 | 2020-05-29 | 121 | 25 | Ali, Nick, Jonathan, Jiaqi
| Read Ballots with Barcodes | 2020-05-10 | 2020-05-15 | 126 | 6 | Jonathan, Jiaqi
| Project Complete | 2020-05-15 | 2020-05-15 | 131 | 1
Presentation
| Design Poster/Prepare for Presentation | 2020-05-16 | 2020-06-05 | 132 | 21 | Ali, Nick, Jonathan, Jiaqi
| Design Slideshow for Presentaion | 2020-05-18 | 2020-06-05 | 134 | 19 | Ali, Nick, Jonathan, Jiaqi
| Practice Presentation Speeches | 2020-06-01 | 2020-06-05 | 148 | 5 | Ali, Nick, Jonathan, Jiaqi
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1