## Basic Gantt Chart
SMART BALLOT BOX GANTT CHART
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | JAN | FEB | MAR | APR | MAY | JUN
Project Planning
| Meet with Sponsor | 2020-01-05 | 2020-01-10 | 0 | 6
| Research Previous Work Completed | 2020-01-10 | 2020-01-14 | 5 | 5
| Research How We Will Add to Project | 2020-01-14 | 2020-01-20 | 9 | 7
| Research Which Proecessor To Use | 2020-01-20 | 2020-01-24 | 15 | 5
| Decide What Items are Wants vs Needs | 2020-01-20 | 2020-01-24 | 15 | 5
| Decide On a Project Schedule and Tasks | 2020-01-24 | 2020-01-31 | 19 | 8
| Decide How to Recreate the SBB with COTS Parts | 2020-02-01 | 2020-02-07 | 27 | 7
| Order Parts | 2020-02-07 | 2020-02-20 | 33 | 14
System Architecture
| Study Exisiting Code Base | 2020-02-21 | 2020-03-01 | 47 | 10
| Redesign the bitstream to Fit Our Porcessor (if needed) | 2020-03-02 | 2020-03-10 | 57 | 9
| Redesign the firmware to Fit Our Porcessor | 2020-03-11 | 2020-03-17 | 66 | 7
| Redesign FreeRTOS to Fit Our Porcessor | 2020-03-25 | 2020-03-31 | 80 | 7
| Redesign SSB Software to Fit Our Porcessor (if needed) | 2020-04-01 | 2020-04-07 | 87 | 7
| Integrate New Parts in to Design | 2020-04-07 | 2020-04-13 | 93 | 7
System Design and Validation
| Test the Functionallity of the Software | 2020-04-13 | 2020-04-26 | 99 | 14
| Test the Functionallity of the Hardware | 2020-04-24 | 2020-05-01 | 110 | 8
| Create Ballots with Barcodes | 2020-05-01 | 2020-05-05 | 117 | 5
MVP Implementation
| Assemble a Working Prototype | 2020-05-05 | 2020-05-19 | 121 | 15
| Read Ballots with Barcodes | 2020-05-10 | 2020-05-19 | 126 | 10
Presentation
| Design Poster for Presentation | 2020-05-18 | 2020-06-01 | 134 | 15
| Design Slideshow for Presentaion | 2020-05-18 | 2020-06-01 | 134 | 15
| Practice Presentation Speechs | 2020-06-01 | 2020-06-08 | 148 | 8
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1